## Sprint 1
Sprint 1 Backlog
| Story | Sprint_Id | Team | Status
Front-End | 1. Create and Planning How To Overwrite Mockup | 1 | Team 2: -Rasyaad -Delvino -Narendra -Izzat | Done
Back-End | 1. Prepare The Technology | 1 | Team 1: -Akmal -Hadiid | Done
| 2. Create ERD | 1 | Team 1: -Akmal -Hadiid | Done
| 3. Listing Feature | 1 | Team 1: -Akmal -Hadiid | Done
| 4. Create Routing Table | 1 | Team 1: -Akmal -Hadiid | Done
| 5. Publish Summary Meeting with StakeHolder | 1 | Team 1: -Akmal -Hadiid | Done

## Sprint 2
Sprint 2 Backlog
| Story | Sprint_Id | Team | Status
Front-End | 1. Prepare and Adding Assets Using Figma | 2 | Team 2: -Rasyaad -Delvino -Narendra -Izzat | Done
| 2. Prepare Ionic and Create Static Navbar | 2 | Team 2: -Rasyaad -Delvino -Narendra -Izzat | Not Yet
| 3. Create Company Profile Unresponsive | 2 | Team 2: -Rasyaad -Delvino -Narendra -Izzat | Not Yet
Back-End | 1. Create Database with Migrations | 2 | Team 1: -Akmal -Hadiid | Done
| 2. Adding Fixed ERD from StakeHolder | 2 | Team 1: -Akmal -Hadiid | Done

## Sprint 3
Sprint 3 Backlog
| Story | Sprint_Id | Team | Status
Front-End | 1. Create Categories Section (without Modal) | 3 | Team 2: -Rasyaad -Delvino -Narendra -Izzat | Done
| 2. Prepare Ionic and Create Static Navbar | 3 | Team 2: -Rasyaad -Delvino -Narendra -Izzat | Done
| 3. Create Company Profile Unresponsive | 3 | Team 2: -Rasyaad -Delvino -Narendra -Izzat | Done
| 4. Delete Ionic Theme Override | 3 | Team 2: -Rasyaad -Delvino -Narendra -Izzat | Done
Back-End | 1. Adding Partner Modules | 3 | Team 1: -Akmal -Hadiid | Done
| 2. Adding Menu Dashboard | 3 | Team 1: -Akmal -Hadiid | Done
| 3. Adding Certificate Modules | 3 | Team 1: -Akmal -Hadiid | Done
| 4. Fixing Certificate Modules and Add to Sidebar | 3 | Team 1: -Akmal -Hadiid | Done
| 5. Adding Social Media Modules | 3 | Team 1: -Akmal -Hadiid | Done
| 6. Adding User Modules | 3 | Team 1: -Akmal -Hadiid | Done

## Sprint 4
Sprint 4 Backlog
| Story | Sprint_Id | Team | Status
Front-End | 1. Create Carousel | 4 | Team 2: -Rasyaad -Delvino -Narendra -Izzat | Done
| 2. Prepare Ionic and Create Static Navbar | 4 | Team 2: -Rasyaad -Delvino -Narendra -Izzat | Done
| 3. Create Company Profile Unresponsive | 4 | Team 2: -Rasyaad -Delvino -Narendra -Izzat | Done
| 4. Delete Ionic Theme Override | 4 | Team 2: -Rasyaad -Delvino -Narendra -Izzat | Done
Back-End | 1. Adding Carousel and Set Up API | 4 | Team 1: -Akmal -Hadiid | Done
| 2. Update Seeder | 4 | Team 1: -Akmal -Hadiid | Done
| 3. Adding API for Social Media Modules | 4 | Team 1: -Akmal -Hadiid | Done
| 4. Adding API for Partner Modules | 4 | Team 1: -Akmal -Hadiid | Done
| 5. Adding Social Media Modules and Resize Preview | 4 | Team 1: -Akmal -Hadiid | Done
| 6. Adding Company Logo Modules | 4 | Team 1: -Akmal -Hadiid | Done
| 7. Adding API for Category Modules | 4 | Team 1: -Akmal -Hadiid | Done